## Front page
Risk assesments for HVL Robotics Førde
Reference: https://forsvaret.no/fakta_/ForsvaretDocuments/Hefte_Risikohaandtering_mai_2012.pdf
| Initial risk |  |  | Remaining risk
| Max | Avg | Min | Max | Avg | Min
Task: Making useful example | 5 | 5 | 5 | 1 | 1 | 1

## HVL Robotics Lab
Risk assesment
Task: Lab work | [5 empty] | Date: 11.07.2019
Performed by: Jarle Alme Aasheim | [5 empty] | Page: 1 of 1
# | Main activity | Danger | Cause | C | P | R | Measures | Rep, Deadline | C | P | R | Note
| Uninformed use | Pushing buttons willie nillie | Open lab, no restriction, | 4 | 2 | 8 | Lab rules on the wall. Safety guidlines. Sign a doc. | Jarle 2019-07-31 | 4 | 1 | 4 | Consider helmets, locking stuff. List emergency numbers. First aid kit. Codes of conduct.
|  | Damaging equipment | Working with new equipment | 3 | 3 | 9 | Using robots at low speed, study manuals |  | 3 | 2 | 6
|  | Collision with people / objects | Unexpected behaviour due to lack of experience | 3 | 3 | 9 | Training and presence of supervisors. Cage around robotarms | MOJO | 3 | 2 | 6
| Working in the lab | Collision with people / objects | New code | 3 | 3 | 9 | Use low speed for first run(30%/T1) | MOJO | 2 | 2 | 4
|  | Sharp objects |  | 4 | 2 | 8 | Use dummy objects | MOJO | 2 | 1 | 2 | No nail guns or other guns, no welding.
|  | Eye / skin damge | Lasers | 3 | 3 | 9 | Training + presence of supervisors | MOJO | 3 | 2
|  | Slipping, tripping, falling | Obstructed view, wet or oily surfaces | 3 | 3 | 9 | Good housekeeping, quality walking surfaces and proper footwear. | DS | 3 | 1 | 3
|  | Overexertion And Repetitive Stress Injuries | Musculoskeletal disorders | 3 | 3 | 9 | Avoid improper lifting, lack of breaks and intensive keying | Self | 3 | 1 | 3
|  | Emergency stop not working | KUKA safety configuration is wrong | 4 | 1 | 4 | Validate safety settings monthly. Add external E-stop on all robots | MOJO, 2019-12-01 | 4 | 1 | 4
|  | Robot safety failure | Hardware / software failure | 4 | 2 | 8 | Validate safety settings monthly | GATES | 4 | 2 | 8
| Working alone | Delays in treating or responding to these emergencies which arise due to a lack of immediate access to first aid or assistance. |  | 4 | 2 | 8 | Lab rules including letting MOJO know when you plan to start and finish | MOJO | 4 | 1 | 4
| Theft | Theft of laptops, robotarms, etc | Criminal activity | 5 | 1 | 5 | Lock doors after leaving | Employees | 5 | 1 | 5
|  | Theft of data, hacking / cracking of robotarm | Criminal activity | 5 | 1 | 5 | Don`t tell students the safety password. Change it from default. Keep robots off internet | MOJO, 2019-12-01 | 5 | 1 | 5
| Misc | Injuries, heartattack etc | Accidents or other | 4 | 2 | 8 | Get first-aid equipment in the office + relevant training | MOJO, 2019-09-01 | 3 | 2 | 6
|  | Fire | Shortcircuits, open flames | 5 | 1 | 5 | Do not block fire exits. Smoke detectors, fire drills | MOJO, 2019-09-01 | 5 | 1 | 5

## Example risk assesment
Risk assesment
Task: Making useful example | [5 empty] | Date: 01.05.2019
Performed by: mojo | [5 empty] | Page: 1 of 1
# | Main activity | Danger | Cause | C | P | R | Measures | Rep, Deadline | C | P | R | Note
1 | Making an assesment | Not caring | Poor focus | 5 | 1 | 5 | Crying | MOJO, 01.06.2019 | 1 | 1 | 1 | This is a note.
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
Remarks
This is going to work brilliantly!

## Template risk assesment
Risk assesment
Task: | [5 empty] | Date: 01.05.2019
Performed by: | [5 empty] | Page: 1 of 1
# | Main activity | Danger | Cause | C | P | R | Measures | Rep, Deadline | C | P | R | Note
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
Remarks