## Front page
Risk assesments for HVL Robotics Førde
Reference: https://forsvaret.no/fakta_/ForsvaretDocuments/Hefte_Risikohaandtering_mai_2012.pdf
| Initial risk |  |  | Remaining risk
| Max | Avg | Min | Max | Avg | Min
Task: Making useful example | 5 | 5 | 5 | 1 | 1 | 1

## HVL Robotics Lab
Risk assesment
Task: Lab work | [5 empty] | Date: 11.07.2019
Performed by: Jarle Alme Aasheim | [5 empty] | Page: 1 of 1
# | Main activity | Danger | Cause | C | P | R | Measures | Rep, Deadline | C | P | R | Note
| Uninformed use | Pushing buttons willie nillie | Open lab, no restriction, | 4 | 2 | 8 | Lab rules on the wall. Safety guidlines. Sign a doc. | Jarle 2019-07-31 | 4 | 1 | 4 | Consider helmets, locking stuff. List emergency numbers. First aid kit. Codes of conduct.
|  | Damaging equipment | Working with new equipment | 3 | 3 | 9 | Using robots at low speed, study manuals |  | 3 | 2 | 6
|  | Collision with people / objects | Unexpected behaviour due to lack of experience | 3 | 3 | 9 | Training and presence of supervisors. Cage around robotarms | MOJO | 3 | 2 | 6
| Working in the lab | Collision with people / objects | New code | 3 | 3 | 9 | Use low speed for first run(30%/T1) | MOJO | 2 | 2 | 4
|  | Sharp objects |  | 4 | 2 | 8 | Use dummy objects | MOJO | 2 | 1 | 2 | No nail guns or other guns, no welding.
|  | Eye / skin damge | Lasers | 3 | 3 | 9 | Training + presence of supervisors | MOJO | 3 | 2
|  | Slipping, tripping, falling | Obstructed view, wet or oily surfaces | 3 | 3 | 9 | Good housekeeping, quality walking surfaces and proper footwear. | DS | 3 | 1 | 3
|  | Overexertion And Repetitive Stress Injuries | Musculoskeletal disorders | 3 | 3 | 9 | Avoid improper lifting, lack of breaks and intensive keying | Self | 3 | 1 | 3
|  | Emergency stop not working | KUKA safety configuration is wrong | 4 | 1 | 4 | Validate safety settings monthly. Add external E-stop on all robots | MOJO, 2019-12-01 | 4 | 1 | 4
|  | Robot safety failure. Table where robot is mounted can break if robot goes at full speed. Safety failure can also result in robot colliding at max speed without its original safety settings. | Hardware / software failure. Students with access to safety password | 4 | 3 | 12 | Validate safety settings monthly. Inform students about risk of changing safety settings. Do not let students do this task alone or unsupervised | GATES | 4 | 2 | 8
| Working alone | Delays in treating or responding to these emergencies which arise due to a lack of immediate access to first aid or assistance. |  | 4 | 2 | 8 | Lab rules including letting MOJO know when you plan to start and finish | MOJO | 4 | 1 | 4
| Theft | Theft of laptops, robotarms, etc | Criminal activity | 5 | 1 | 5 | Lock doors after leaving | Employees | 5 | 1 | 5
|  | Theft of data, hacking / cracking of robotarm | Criminal activity | 5 | 1 | 5 | Don`t tell students the safety password. Change it from default. Keep robots off internet | MOJO, 2019-12-01 | 5 | 1 | 5
| Misc | Injuries, heartattack etc | Accidents or other | 4 | 2 | 8 | Get first-aid equipment in the office + relevant training | MOJO, 2019-09-01 | 3 | 2 | 6
|  | Fire | Shortcircuits, open flames | 5 | 1 | 5 | Do not block fire exits. Smoke detectors, fire drills | MOJO, 2019-09-01 | 5 | 1 | 5

## Example risk assesment
Risk assesment
Task: Making useful example | [5 empty] | Date: 01.05.2019
Performed by: mojo | [5 empty] | Page: 1 of 1
# | Main activity | Danger | Cause | C | P | R | Measures | Rep, Deadline | C | P | R | Note
1 | Making an assesment | Not caring | Poor focus | 5 | 1 | 5 | Crying | MOJO, 01.06.2019 | 1 | 1 | 1 | This is a note.
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
Remarks
This is going to work brilliantly!

## Template risk assesment
Risk assesment
Task: | [5 empty] | Date: 01.05.2019
Performed by: | [5 empty] | Page: 1 of 1
# | Main activity | Danger | Cause | C | P | R | Measures | Rep, Deadline | C | P | R | Note
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
Remarks